## 19-20 trajectory
Type | Address | Settlement | Capacity | LP allocation | Planning Application References | PCO change | 2018/19 Contact | 2018/19 Notes from contact | Officer Notes | Justifications and evidence for completion assumptions | Expected Start Date | 18/19 completions | Units left 18/19 | 19/20 N/S | 19/20 U/C | 19/20 B | Units left 19/20 | Comments 2019/20 | notes from contact | Contact | Contact Email | 2020/21 Year 1 | 2021/22 Year 2 | 2022/23 Year 3 | 2023/24 Year 4 | 2024/25 Year 5 | 2025/26 Year 6 | 2026/27 Year 7 | 2027/28 Year 8 | 2028/29 Year 9 | 2029/30 Year 10 | 2030/31 Year 11 | 2031/32 Year 12 | 2032/33 Year 13 | 2033/34 Year 14 | 2034/35 Year 15 | 2035/36 Year 16 | 2036/37 Year 17 | 2037/38 Year 18 | Total | Units carried over beyond 2036
LP Allocation | Field OS 6604, Nottingham Road | Ab Kettleby | 9 | ABK1 | 18/01419/OUT (9) |  | Andrew Granger (Adam Murray) | They are updating the layout to meet concerns, the issues they are facing are: planning process timescales and they want to sell the site to potential developers | permission now granted - DC 27.08.2019. amended from 10 to 9 dwellings. Found for sale online for £900k-£1m - newly offered to market -added online for sale in June 20 | land needs to be sold to developer, REM needs to be worked up and submitted (assume within 3 years and + 3 years max to SOS); land could come forwards quickly or slowly, depending on sale; conservative estimates have been made based on fact that majority of plots sit on facing main A road (less attractive than other small rural site alternatives) and high plot costs (in region of £100k per plot) currently being marketed as well as current market/economic uncertainty highlighted by developer | beyond 5 years |  | 9 | 9 | 0 | 0 | 9 | [10 empty] | 2 | 7 | [10 empty] | 9 | 0
LP Allocation | Field No 0070, Station Lane | Asfordby | 100 | ASF1 | 16/00373/REM (100) |  | Brp Architects (Christopher Woods) |  | both recorded 45 completions this year however, we recorded 7 completions for last year, Jelsons recorded 12, added 5 into this years completions as not previously counted; last years total number for units on site did not add to 100? (87+7 = 94 - missing 6 units?) | partially complete, on site and expected to finish in 21/22 | U/C | 7 | 93 | 9 | 34 | 50 | 43 |  |  |  |  | 33 | 10 | [16 empty] | 43 | 0
LP Allocation | Field OS 6934, Bypass Road | Asfordby | 55 | ASF2 | 19/01291/REM (PERS106) |  | Gary Kirk | Sold to Mather Jamie and the REM will be soon. Commencement expected around 7 months after REM | Affordable housing/RP led scheme, Deeley DPP3 delivery partner for RPs. REM 040620 committee approval, pending DN | REM application permitted; AH led scheme provides greater certainty on delivery | less than 12 months |  | 55 | 55 | 0 | 0 | 55 | [5 empty] | 55 | [16 empty] | 55 | 0
LP Allocation | Field OS 0070, Hoby Road | Asfordby | 70 | ASF3 | 18/01517/REM (70) |  | Jelson (Rob Thorley) | Second phase ASF1 | DN 0919. VAR s106 being processed to move some affordable to Melton KEVII, discharging conditions apps submitted in Jan 20. | Delivery considered in context of overall company site delivery in ASF and KEVII. Inputted developer proposed delivery as reasonable given above and DN date | 2-3 years |  | 70 | 70 | 0 | 0 | 70 | [6 empty] | 39 | 31 | [14 empty] | 70 | 0
LP Allocation | Land Adj Crompton Road - ASFH1 phase 2 | Asfordby Hill | 16 | ASFH1 part | 17/00821/FUL (16) | 59 | Harris Lamb (Sam Silcocks) | No information collected but FUL application | 20/00770/VAC 0720 - Ironbridge Development (East Midlands) Ltd | developer led s73 Variation PCO, assumed as stated by agent due to strong wording on delivery commitment. Total site phasing on basis of 14-16 dpa (based on providing consistent average annual supply of site coming forwards assuming lower site figures still for phases 3 and 4; may rise to 16- 25dpa if wider site PCO OUT is permitted) | less than 12 months |  | 16 | 16 | 0 | 0 | 16 | [5 empty] | 16 | [16 empty] | 16 | 0
LP Allocation (w/o PP) | Land to rear of Adjacent To 23 And 24, Glebe Road - ASFH 1 phase 3 | Asfordby Hill | 9 | ASFH1 part | 20/00470/OUT (PCO) | 16 | Harris Lamb (Sam Silcocks) | Assuming fasing | likely to be significantly more than 9 units - ask developer - ASH1 (part) remaining PCO 25 units. PCO ENQMG from Keepmoat homes re phases 3 and 4 0 - demonstrates potential developer interest | whilst still PCO numbers not revised upwards; retained as 9 with delivery on 22/23 in line with peak delivery of scheme and assumptions have been made with consideration of overall phasing of site phases 2-4. strong wording on delivery commitment from agent (based on providing consistent average annual supply of site coming forwards assuming lower site figures still for phases 3 and 4; may rise to 16- 25dpa if wider site PCO OUT is permitted) | 1-2 years |  | 9 | 9 | 0 | 0 | 9 | [6 empty] | 9 | [15 empty] | 9 | 0
LP Allocation (w/o PP) | Land off Stanton Road | Asfordby Hill | 47 | ASFH2 | 20/00470/OUT (PCO) |  | Harris Lamb (Sam Silcocks) | Assuming fasing of ASFH1 | ASH2 PCO - 75 units (PCO ENQMG from Keepmoat homes) re phases 3 & 4 - demonstrates potential developer interest | whilst still PCO numbers not revised upwards to 75; retained as 47 with delivery from 22/23 (in line with phase 3 (see ASFH1 part) delivery spread across 4 years as per info provided but delayed by 1 year to achieve more consistent average site phasing across phases 2-4. strong wording on delivery commitment from agent, (based on providing consistent average annual supply of site coming forwards assuming lower site figures still for phases 3 and 4; may rise to 16- 25dpa if wider site PCO OUT is permitted) | 1-2 years |  | 47 | 0 | 0 | 0 | 47 | [6 empty] | 5 | 14 | 14 | 14 | [12 empty] | 47 | 0
LP Allocation (w/o PP) | Land Rear Of Daybells Farms, Grantham Road | Bottesford | 41 | BOT1 | 17/00250/OUT (Part - PCO 18) |  | HSSP | Section 106 still to be finalised – land will be disposed of once agreement is in place; trajectory unknown at this time | looking to increase to 23/4; corres with officer and agent 0120; the OUT PCO is only for part of the site | OUT still pending s106; may req new FUL/OUT for revised plans and will require REM at min; evidence revised plans being looked at by agent but not yet submitted; no clarity that new plans for higher number are achievable; revisions may result in delays to progress scheme; however developer on board to deliver scheme and leading revised plan, providing impetus. moved delivery forwards from 21/22 to 22/23 as a consequence of need for new permissions; note no evidence that rest of site is being progressed, likely to be later in LP period via separate application and will require splitting of site into 2 blocks (ownership of second parcel is local housing trust and private individual), site therefore split into 2 delivery blocks with second block assumed for 29/30 SOS post delivery of other sites in BOT which are currently being progressed | 2-3 years |  | 41 | 0 | 0 | 0 | 41 | [6 empty] | 18 | [7 empty] | 12 | 11 | [6 empty] | 41 | 0
LP Allocation | Field 6967, Grantham Road | Bottesford | 60 | BOT2 (part) | 19/00573/REM |  | Marrons (Joanne Althorpe) | Actively working towards REM | DN 280120; agent Tom.Collins@nineteen47.co.uk | SOS in Mar 20; COVID pause; state to restart Jul 20; work programme at advanced stage; transposed delivery as stated by developer as considered reasonable and deliverable within those timeframes | less than 12 months |  | 60 | 60 | 0 | 0 | 60 | [5 empty] | 32 | 28 | [15 empty] | 60 | 0
LP Allocation | The Old Clay Pit, Grantham Road | Bottesford | 40 | BOT2(part) | 17/01577/OUT |  | Davidsons (instead of nineteen47) | Still trying to conclude the s106 on the outline but assuming it will be resolved shortly | 080719 DN; email to Helen Prangley as per last year | currently preparing REM don’t assume completions untiled 21/22 which seems reasonable timeframe, slight shift forwards from last year | 1-2 years |  | 40 | 40 | 0 | 0 | 40 | [6 empty] | 5 | 35 | [14 empty] | 40 | 0
LP Allocation (w/o PP) | Land West Of Rectory Farm | Bottesford | 163 | BOT3 | 20/00388/OUT (PCO 215) | 52 | Colin Wilkinson | Towards PA. Pre-application process has begun and most survey work is complete. Still trying to address Historic England and noise issues. No change in terms of build rates. | 20/00388/OUT for 215 significant increase on 163 allocated for site; approx. 1/3 increase | new OUT (PCO) suggest site come forward within next 5 years. Figures not adjusted to new OUT numbers unless OUT permitted so still assumed 163 at developer stated rate of 30dpa. Assume 2-3 years to SOS as reasonable, as OUT only just submitted, (sale, REM and DIS etc. Still required before SOS) moving completions forwards by 2 years on that stated. | 2-3 years |  | 163 | 0 | 0 | 0 | 163 | [7 empty] | 30 | 30 | 30 | 30 | 30 | 13 | [9 empty] | 163 | 0
LP Allocation | OS Fields 8456 7946 And 9744, Normanton Lane | Bottesford | 97 | BOT4 | 19/00588/REM (97) |  | Miller Homes Limited and Richborough Estates (Clare Thorton) | Commencing on 4th April | new REM for 97 submitted and approved up from 88 dwellings; 16 BC final notices for site before end mar 20 | mismatch between site visit AM and developer information, considered to be due to difference in definition of completed (practically complete) retained AM visit numbers for progress on site after discussion with SH. Remaining completions are entered as per developer estimated after adjusting for this years AM completions) | U/C |  | 97 | 60 | 9 | 28 | 69 |  |  |  |  | 25 | 29 | 15 | [15 empty] | 69 | 0
LP Allocation (w/o PP) | Land West Of Saltby Road And South Of Mill Lane, Saltby Road | Croxton Kerrial | 39 | CROX1 | 17/00299/OUT (PCO) |  | Colin Wilkinson | S106 Agreement yet to be completed, but developer is on board. | S106 query passed to LP to progress at agents request. Owned by Belvoir Estate as is all land around the village | OUT still pending s106 agreement. Req sale to developer and REM permission, largest site in village in MLP. Estate concerns re CV19; moved delivery stated forwards by one year at 20dpa rate | 3-4 years |  | 39 | 0 | 0 | 0 | 39 | [7 empty] | 20 | 19 | [13 empty] | 39 | 0
LP Allocation (w/o PP) | Land East of Saltby Road & South of A607 | Croxton Kerrial | 10 | CROX2 |  |  | Colin Wilkinson | No progress to date. | No update or progress reported, appears to be least advanced of 3 schemes. Owned by Belvoir Estate as is all land around the village | Beyond 5YHLS as no action taken to bring site forwards, competition from other developments within village from Estate land; delivery expected after completion of CROX1 & CROX3 | beyond 5 years |  | 10 | 0 | 0 | 0 | 10 | [11 empty] | 10 | [10 empty] | 10 | 0
LP Allocation (w/o PP) | Land South of Main Street (A607) and west of the Nook | Croxton Kerrial | 10 | CROX3 |  |  | Colin Wilkinson | Trying to reach agreement with GP surgery regarding car park. Outline planning application in 2019/20. | Owned by Belvoir Estate as is all land around the village | no permission in place, insufficient evidence to support delivery within next 5 years, left delivery in same position from last year | beyond 5 years |  | 10 | 0 | 0 | 0 | 10 | [10 empty] | 10 | [11 empty] | 10 | 0
LP Allocation (w/o PP) | Easthorpe Lodge, Manor Road | Easthorpe | 9 | EAST1 (Part) | 20/00295/FUL (PCO) (21/47) | 12 | Marrons (Joanne Althorpe) | Agent unable to contact client - using previous information where site was being marketed. OUT < 9 units | current pp 15/01016/OUT for 9 dwelling. '20/00295/FUL (PCO) for EAST1 and EAST2; 47 total plus conversion of existing large house into 3 dwellings = total 50 dwellings [EAST1 = 21 + separate pp for 3 conversion | SOS for conversions. Development funded; REM PCO. Figures not revised until REM decided; build rate as per developer stated (total 20 for 2021/22) | less than 12 months |  | 9 | 9 | 0 | 0 | 9 | [5 empty] | 9 | [16 empty] | 9 | 0
LP Allocation | Easthorpe Lodge, Manor Road | Easthorpe | 3 | EAST1 (Part) | 19/01340/FUL (3) |  | Marrons (Joanne Althorpe) | Agent unable to contact client - using previous information where site was being marketed. OUT < 9 units | Conversion of existing large house into 3 dwellings within EAST1 (19/01340/FUL). Net 2 increase | SOS | U/C |  | 3 | 0 | 3 | 0 | 3 |  |  |  |  | 3 | [17 empty] | 3 | 0
LP Allocation (w/o PP) | OS Field Number 0349, Manor Road | Easthorpe | 18 | EAST2 | 20/00295/FUL (PCO) (26/47) | 8 | Marrons (Joanne Althorpe) | Agent unable to contact client - using previous information. Site being marketed, likely to be developed alongside EAST1 | Formerly 17/00996/OUT (18); 20/00295/FUL (PCO) for EAST1 and EAST2; 47 total [EAST2 = 26 dwellings] | SOS for conversions. Development funded; REM PCO. Figures not revised until REM decided; build rate as per developer stated (total 20 for 2021/22) | less than 12 months |  | 18 | 18 | 0 | 0 | 18 | [5 empty] | 11 | 7 | [15 empty] | 18 | 0
LP Allocation | Land off Great Lane | Frisby On The Wreake | 53 | FRIS1 | 17/01325/REM (53) |  | Be1 Architects (Ny Moughal) | Subject to DIS, they are ready to start on site (October 2018) - Still have not started (April 2019) | final BC cert for 36 dwellings issued | Under construction, mainly completed, assumed works programme to complete in 20/21 correct given advanced stage of development even if CV19 delays | U/C |  | 53 | 1 | 15 | 37 | 16 |  |  |  |  | 16 | [17 empty] | 16 | 0
LP Allocation | Land At Water Lane | Frisby On The Wreake | 22 | FRIS2 | 16/00740/OUT (22) |  | Landmark Planning Limited (Peter Wilkinson) | Judicial Review period | SEC state decided not to call in for JR (20.3.19). Response to 20/00340/ENQG sent 220520; potential plan and policy conflict for 9 self build plots against 22 scheme development. | no clear scheme or way forward for site. Developer wants to reduce to 9 large self build dwellings. Numbers not revised as yet. Requires new permission to change proposal. Interest in site suggests just beyond 5 year appropriate | beyond 5 years |  | 22 | 22 | 0 | 0 | 22 | [8 empty] | 11 | 11 | [12 empty] | 22 | 0
LP Allocation | Land South Of Frisby On The Wreake, Leicester Road | Frisby On The Wreake | 48 | FRIS3 | 16/00704/OUT (48) |  | Bowbridge Homes (Oliver Purday) | Towards REM - expected to be submitted in the next 3 months | Bowbridge homes new owners. REM still pending. Long term outstanding s73 to vary to include self build plots (19/00605/VAC), expect this to be addressed by REM. Inclusion of self build plots may stretch out delivery PCO REM | still pending submission of new REM, expected soon. Since REM not yet submitted moved 10/30 of 21/22 developer stated delivery to 22/23 | 1-2 years |  | 48 | 48 | 0 | 0 | 48 | [5 empty] | 20 | 28 | [15 empty] | 48 | 0
LP Allocation (w/o PP) | Land At Holme Farm, Rearsby Lane | Gaddesby | 14 | GADD1 | 19/01303/FUL (PCO) |  | HSSP | Towards REM | previously 15/00361/OUT (14); Helen Prangley agent - Charnwood Development Ltd. New FUL. Additional new email sent to Helen Prangley awaiting response | Site sold to Charnwood Developments ltd. | 1-2 years |  | 14 | 14 | 0 | 0 | 14 | [5 empty] | 7 | 7 | [15 empty] | 14 | 0
LP Allocation | Land North Off Pasture Lane | Gaddesby | 11 | GADD2 | 18/00145/OUT (11) |  | HSSP (Nick Cooper) | Site being marketed at the moment |  | REM application instructed, not yet submitted. No developer on board. Allow time for sale of site and possible review | 3-4 years |  | 11 | 11 | 0 | 0 | 11 | [7 empty] | 5 | 6 | [13 empty] | 11 | 0
LP Allocation (w/o PP) | Land OS 469098 313572, Pasture Lane, Gaddesby | Gaddesby | 11 | GADD3 | 20/00591/OUT (PCO 10) | -1 | Andrew Gamble | Currently preparing outline application, hoping to submit within the next 3-4 weeks. Not in a position to give any approximations for this as we still have to gain the outline planning. We then need to negotiate with the developer. | 20/00591/OUT submitted 02.06.2020 | delivery adjusted to take into account OUT PCO and need for future REM. No. not adjusted to 10 until OUT decided. | 2-3 years |  | 11 | 0 | 0 | 0 | 11 | [7 empty] | 11 | [14 empty] | 11 | 0
LP Allocation (w/o PP) | OS 4240, Burdetts Close | Great Dalby | 37 | GREA1 | 19/01376/OUT (PCO 35) | -2 | Define Planning & Design Ltd (Mark Rose) | They key issue for us is that we are waiting for the Council to respond on the Section 106. There is a developer waiting to purchase the site once that is finalised and the permission issued. If that delay can be addressed in the near future, then given the relatively small size of the site, I would expect it to be completed in the period 2019/20 (20 dwellings) - 2021/22 (17 dwellings). | 18/00721/OUT JR court case pending - delay due to CV19; new 19/01376/OUT | OUT still s106 pending; site has not been marketed yet, no developer identified/interest. REM will still be required, then DIS etc.; expect site may come forwards with SOS in-between next 2 and 6 years, with delivery thereafter. CV19 market insecurity re sale of land and slightly higher perceived risk profile given JR and community opposition, put site delivery assumptions for SOS beyond 5 years. not revised 37 down to 35 until DN released | beyond 5 years |  | 37 | 37 | 0 | 0 | 37 | [8 empty] | 10 | 20 | 7 | [11 empty] | 37 | 0
LP Allocation | Allotment Gardens, Boyers Orchard | Harby | 15 | HAR1 | 19/00233/REM (15) |  | HSSP (Samantha Griffiths | Application for reserved matters submitted but progress being delayed by planning – housing mix / viability issues. Scheme hopefully to be approved late summer to enable infrastructure to commence. | formerly 15/00942/OUT; 19/00233/REM DN 12.2.20 | Agent states Autumn 2020 SOS, suggesting 2021/22 for first completions; dates depend on awaited completion of S106 agreement | 1-2 years |  | 15 | 15 | 0 | 0 | 15 | [5 empty] | 8 | 7 | [15 empty] | 15 | 0
LP Allocation | Long Clawson Dairy, 7 Langar Lane | Harby | 12 | HAR2 | 15/00933/FUL (12) |  | Chave Planning (Caroline Chave) |  | Last years AM stated 3 remained UC on site, the rest completed; site visit stated 10 completed this year? altered to 3 completions for this year. Site now completed | built | Built | 3 | 3 | 0 | 0 | 3 | 0 | [22 empty] | 0 | 0
LP Allocation | Millway Foods Ltd , Colston lane | Harby | 53 | HAR3 | 19/01384/REM (PCO) |  | Nigel Griffiths | Unable to contact | on file corres re PCO REM show that some issues still need to be addressed; long delay to get to committee but progress continues to be made towards taking it to com for decision; AH RP take on issue. | REM application PCO; assumes that REM achieved within 12 months and SOS within 3 years; completions from yr. 4 | 2-3 years |  | 53 | 53 | 0 | 0 | 53 | [7 empty] | 13 | 30 | 10 | [12 empty] | 53 | 0
LP Allocation (w/o PP) | Land Around Sherbrook House And Millway Foods, Colston Lane | Harby | 61 | HAR4 | 18/01183/FUL (PCO 61) |  | Marrons Planning (Andrew Gore) | A full application was submitted in September 2018 (after 16/00318/OUT (50)). This application (now for 65 dwellings) is expected to go to committee in May/June this year with a recommendation for approval. Please see the projected number of dwellings to be built per year below- | consent permitted subject to several delegated amendments, which are currently being negotiated | Need to resolve FUL delegated matters, still pending from 260919 committee decision to permit subject to; no progress for some time, suggests no urgency to get developing. stated +2 years SOS considered reasonable; completions following year at stated build rate max of 20dpa | 2-3 years |  | 61 | 61 | 0 | 0 | 61 | [6 empty] | 20 | 20 | 20 | 1 | [12 empty] | 61 | 0
LP Allocation (w/o PP) | Land off Canal Lane | Hose | 41 (16+25) | HOS1 | 19/00859/OUT (PCO 34) | -7 | Andrew Granger (Adam Murray) | Phase 2 of 15/00944/OUT | formerly 17/00401/OUT & 15/00944/OUT; overall proposed reduction in units from 41 to 34. Two part HOS1 applications have been combined together as per PCO, site clearly in single ownership/planned development. Due to go to committee JUL with PER; AH and Viability have held this up for 1 year; not to be decided at OUT, suggests potential to delay REM application when it comes forwards | Still only OUT PCO. REM will still be required. numbers not adjusted until new permission granted, new permissions, S106 and REM delay SOS from developer stated completions in 2021/22 moved to 22/23; using developer stated their 20dpa completion rate with 50% completions in first year | 2-3 years |  | 41 | 41 | 0 | 0 | 41 | [6 empty] | 10 | 20 | 11 | [13 empty] | 41 | 0
LP Allocation | Grange Farm House, Harby Lane | Hose | 35 | HOS2 (part) | 18/00500/OUT (35) |  | HSSP (Nick Cooper) | Site not marketed yet, client considering options | DN 180320 for phase 1; phase 2 submitted for additional 35 dwellings - 20/00397/OUT (38); would bring total on site to 73; site split into 2 phases at this stage to reflect how site is being considered | landowner states that wish to market site as a whole when phase 2 has been granted permission, this will delay marketing of site, a REM will be required post sale of site. Taken into consideration HOS1 delivery, expect HOS2 to follow HOS1 which is at a more advanced stage, with delivery following on from HOS1 | beyond 5 years |  | 35 | 35 | 0 | 0 | 35 | [8 empty] | 17 | 18 | [12 empty] | 35 | 0
LP Allocation (w/o PP) | Land South Of Grange Farm, Harby Lane | Hose | 0 | HOS2 (part) | 20/00397/OUT (PCO 38) | 38 | HSSP (Nick Cooper) | Site not marketed yet, client considering options | phase 2 for 38 dwellings submitted April 20, note significant objections being raised re effectively doubling dwellings on LP allocation | No delivery has been added into the trajectory for this site at this stage as the dwellings within Phase 1 fulfil the total LP anticipated allocation; will not be revised until a DN is issued; but added in as a row to ensure monitoring of this site is included as and when decision is made re phase 2 and to reflect this unpermissioned section of the LP allocation, OUT needs to be secured before site can be marketed alongside phase 1 to developers. expect any delivery to follow on after completion of phase 1, beyond next 5 years | beyond 5 years |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0 | 0
LP Allocation | Field No 7858, Melton Road | Long Clawson | 10 | LONG1 | 19/01072/FUL (10) |  | HSSP (M Etchells) | Land sale still not agreed – outline approval expires 3 March 2020 | 15/00547/OUT now 19/01072/FUL per s106 - DN 19/03/20; now Pelham Architects/Waters Homes Ltd - info@watershomes.co.uk. Website is promoting development - brochure online - called Mill View | states will SOS summer 2020 and completed before Mar 21; tight development timeframe, as not yet SOS adjusted for half complete into 21/22 | less than 12 months |  | 10 | 10 | 0 | 0 | 10 |  |  |  |  | 5 | 5 | [16 empty] | 10 | 0
LP Allocation | Land Rear Of 1 To 3, Hickling Lane | Long Clawson | 31 | LONG2 | 16/00810/OUT (31) (PERS106) | 0 | Andrew Granger (Adam Murray) | It is owned by the developer and there is a need to submit the REM, with issues related to the planning process (timescales) | PERS106 200619, s106 still pending | as recommended | 4-5 years |  | 31 | 31 | 0 | 0 | 31 | [7 empty] | 5 | 15 | 11 | [12 empty] | 31 | 0
LP Allocation | Birleys Garage, 1 Waltham Lane | Long Clawson | 45 | LONG3 | 16/00560/OUT (45) |  | Ben Hunt Planning (Ben Hunt) | Unable to contact | DN 190220 | OUT secured. Ambitions to bring forwards within next 2 years but uncertainty regarding the delivery and no developer on board yet. Still requires REM post finding developer to bring forwards | 4-5 years |  | 45 | 45 | 0 | 0 | 45 | [8 empty] | 15 | 15 | 15 | [11 empty] | 45 | 0
LP Allocation | Field Numbers 5855 And 6071, Nottingham Road | Melton Mowbray | 85 | MEL1 | 17/00711/REM (85) |  | Davidsons Homes (Matthew Sanders) |  |  | U/C; nearly built out | U/C | 12 | 65 | 0 | 22 | 51 | 22 |  |  |  |  | 22 | [17 empty] | 22 | 0
LP Allocation (w/o PP) | Land adjacent to St Bartholomew's Way and Horseguard Way | Melton Mowbray | 70 | MEL10 |  |  | Defence Infrastructure Organisation (Christine Ide) | After a conversation with somebody else in the MOD (local), they are not expecting to develop this land due to its high quality for grazing | No evidence of any actions being undertaken or planned in relation to this site. Retained to come forwards at end of the plan period as per previous trajectory, considered at least to come forwards after MEL3 as direct competition |  | beyond 5 years |  | 70 | 0 | 0 | 0 | 70 | [17 empty] | 10 | 30 | 30 |  |  | 70 | 0
LP Allocation | King Edward Vii Upper School, Burton Road | Melton Mowbray | 120 | MEL2 (part) | 18/00200/REM (120) |  | Jelson (Rob Thorley) | REM just approved (April 2019) | Main application 120 plus conversions of retained buildings 18/00201/FUL (13) and 18/00202/FUL (4)]; total 137 on allocated site | on site and works begun, assuming max of 40dpa on site, taking into consideration conversions within other parts of overall site, new build only phase 1 assumed due to location of conversions on site | less than 12 months |  | 120 | 120 | 0 | 0 | 120 | [5 empty] | 40 | 31 | 32 | 17 | [13 empty] | 120 | 0
LP Allocation | King Edward Vii Upper School, Burton Road | Melton Mowbray | 13 | MEL2 (part) | 18/00201/FUL (13) |  | Jelson (Rob Thorley) |  | Main application 120 plus conversions of retained buildings 18/00201/FUL (13) and 18/00202/FUL (4)]; total 137 on allocated site | on site and works begun, this application is in centre of site, assumed to come forwards in mid phase of development | less than 12 months |  | 13 | 120 | 0 | 0 | 13 | [6 empty] | 9 | 4 | [14 empty] | 13 | 0
LP Allocation | King Edward Vii Upper School, Burton Road | Melton Mowbray | 4 | MEL2 (part) | 18/00202/FUL (4) |  | Jelson (Rob Thorley) |  | Main application 120 plus conversions of retained buildings 18/00201/FUL (13) and 18/00202/FUL (4)]; total 137 on allocated site | on site and works begun, this application is in corner of site, assumed to come forwards in later phase, update next year when phasing is more obvious | less than 12 months |  | 4 | 120 | 0 | 0 | 4 | [7 empty] | 4 | [14 empty] | 4 | 0
LP Allocation | Land At South Of Hill Top Farm, St Bartholomews Way | Melton Mowbray | 83 | MEL3 | 19/00342/FUL (83) |  | Marrons (Joanne Althorpe) | The application aims to put together three OUT approved applications, so it can be quick to be determined | DN 040220; letter in app file to state relevant works commencement 240320 onwards. | clear application is progressing DIS and BC IN etc., states that 10 U/C; Davidsons other close by site MEL1 close to completing; therefore taken as recommended | U/C |  | 83 | 83 | 10 | 0 | 83 |  |  |  |  | 40 | 43 | [16 empty] | 83 | 0
LP Allocation (w/o PP) | Top End Cattle Market | Melton Mowbray | 26 | MEL4 |  |  | Pranali Parikh | MBC landowner, no decision has been made to date to develop or dispose, currently being assessed as part of wider asset review for proposed housing company/MBC HRA development. Expect additional information over the course of 2019/20 as asset review concludes and new priorities for development are established post election. | No action taken to bring forward site, not committee decision/resolution to dispose | Beyond 5YHLS | 4-5 years |  | 26 | 0 | 0 | 0 | 26 | [9 empty] | 13 | 13 | [11 empty] | 26 | 0
LP Allocation | Catherine Dalley House, Scalford Road | Melton Mowbray | 56 | MEL5 | 18/00518/FUL (56) |  | The Planning Bureau (Neil Martin) | Development for 56 units, which will give 40 additional dwellings to the anticipated capacity. PCO Unable to contact | Site works well underway at time of site visit; minor new application to change housing mix (18/00518/FUL with DN 30.8.19; new 19/01354/FUL (PCO)) Not available to buy on website states UC | Under Construction, foundations and some brick work completed, state that site closed for rest of year and slower rate build out when recommence; assumes that completions will have to move to 21/22 | U/C |  | 56 | 0 | 56 | 0 | 56 | . |  |  |  |  | 56 | [16 empty] | 56 | 0
LP Allocation (w/o PP) | Land fronting Dieppe Way, Scalford Road | Melton Mowbray | 37 | MEL6 |  |  |  | Probably the option agreement has expired and there is no active lead on this allocation at present. | 08/00650/OUT (WDR) for reference. Land options agreement expired some years ago. No agent or developer looking to put together proposal. MBC ownership of ransom strip to Dieppe Way, alt access possible through Jelson owned ransom strip to Tennyson Way (previous developers not able to negotiate access via this preferential route). Richard Shaw happy to be contacted annually if no other contact found. | private allotment land in multiple ownerships, complex site to but together; no land option agreement, no developer or person trying to put together any proposal. Delivery assumed for last 5 years of plan period; site boarders Fairmead, not a desirable location to develop compared to other sites and landowners have high expectations, random strip to either site of site (MBC and Jelson owns them) other sites to Dieppe way all AH, private sector failure on site next door (barratts sold on to RP at late stage of development as could not sell in last economic decline circa 2009 to Riverside as shared ownership scheme), but AH providers not considered likely to be able to put complex site together to bring forwards for development - considered more likely to come forwards towards end of period if at all or if lack of other deliverable and available sites. potential review site to removed as LP allocation as not deliverable | beyond 5 years |  | 37 | 0 | 0 | 0 | 37 | [18 empty] | 19 | 18 |  |  | 37 | 0
LP Allocation (w/o PP) | Land at Thorpe Road | Melton Mowbray | 16 | MEL7 | 19/00909/OUT (PCO 46) | 30 | Homes England | Part of Homes England pipeline for disposal. Expected to be on the Market: Q2 2019/20. Site Ref 12444. Expect to only be able to gather information on delivery post sale. | Site sold by Homes England via tender 0320 to Snowden Homes; Homes England OUT Permission due to be decided in 0620 committee postponed from 280520. He deliverability criteria as part of tender | REM still required. HE require deliverability. OUT nearly resolved. S106 still required. No. dwellings not changed until OUT decided. Mar 21 earliest SOS, so moved into 21/22 SOS; completions 18 months after due to demolition/brownfield/historic nature (assumes more extensive pre commencement works) | 2-3 years |  | 16 | 0 | 0 | 0 | 16 | [7 empty] | 12 | 4 | [13 empty] | 16 | 0
LP Allocation | Beebys Yard, Burton Street | Melton Mowbray | 4 | MEL8 | 19/01175/FUL (4) |  | Shouler And Son (Simon Shouler) | Has consent but is not being marketed | Formerly 08/00326/FUL (11) but 19/01175/FUL for 4 dwellings U/C - a revised app for 4/11 units. Site visit, works to convert underway | 19/01175/FUL under construction for alms house charity use. Rest of site being renovated for ongoing commercial use | U/C |  | 4 | 0 | 4 | 0 | 4 |  |  |  |  | 4 | [17 empty] | 4 | 0
LP Allocation (w/o PP) | Wycliffe House, Snow Hill | Melton Mowbray | 20 | MEL9 |  |  | Neil Jeffery | Conversation with owner - he wants to progress but there is some lack of understanding of the planning process. Information with agents and developers sent. Information to the Regen team sent. Information to Celia re: RPs sent. | No progress; owner not demonstrated site is being brought forwards for development for long time (last local plan period), potential site to be removed from allocations at LP review as non deliverable | Site has not progressed fro number of years, no evidence landowner is proactively looking to bring forwards site, assumes beyond 5YHLS and most likely to be towards end of plan period, potential to link with reserve site at Snow Hill, therefore assumes end of plan period | beyond 5 years |  | 20 | 0 | 0 | 0 | 20 | [18 empty] | 10 | 10 |  |  | 20 | 0
LP Allocation (w/o PP) | Spinney Road (remainder) | Melton Mowbray | circa 480 | NSN (part) |  |  | Taylor Wimpey | It is expected to phase-deliver alongside or after the site with planning permission is delivered | Evidence is speculative at this point given need to finalise masterplan | based on that provided by developer, moved delivery on by 1 year than stated by developer due to phase 1 delivery, assuming a 50 dpa site capacity also on phase 1 (therefore developed over next 4 years) with this site phase 2 coming on line from year 6 not year 5 once phase 1 completes | 4-5 years |  | 480 | 0 | 0 | 0 | 480 | [8 empty] | 7 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 43 |  |  |  | 480 | 0
LP Allocation (w/o PP) | Barwood | Melton Mowbray | 550 | NSN (part) |  |  | Barwood | Not much progress, it is expected to deliver later in the trajectory (concerns from Homes England as they are not delivering as expected in other areas) | Evidence is speculative at this point given need to finalise masterplan | still at very early stage, significant variables and potential issues to delay delivery e.g. MMDR and current delays sorting s106; First completions envisaged for end of Q423, moved to Q124 given potential issues to delay; mirrored pattern of delivery stated by developer of a max 100dpa alongside initial reduced levels to reflect building up capacity and to reflect competition with other developments in NSN | 4-5 years |  | 550 | 0 | 0 | 0 | 550 | [8 empty] | 50 | 75 | 75 | 100 | 100 | 100 | 50 | [7 empty] | 550 | 0
LP Allocation (w/o PP) | Land North John Ferneley College | Melton Mowbray | 400 | NSN (part) | 18/00769/OUT (PCO) |  | Richborough | Education needs to comment for a common s106 (alongside LCC site). Meeting in two weeks (mid May). Assumption this will be resolved | issues re S106 as shared with LCC site to south, where impetus to get it signed has been reduced (LCC state withdrawn site form market); | developer on board to bring forwards pending REM; assumed as provided 40dpa delivery. Risk to s106 securing and REM within time frame assumed, therefore assume delivery from 22/23 (not 5 in 21/22 and only 25 not 35 in 22/23 then 40dpa thereafter as per advised) | 1-2 years |  | 400 | 0 | 0 | 0 | 400 | [6 empty] | 25 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 15 | [5 empty] | 400 | 0
LP Allocation (w/o PP) | Sysonby Farm, Nottingham Road | Melton Mowbray | 290 | NSN (part) | 18/00359/OUT (PCO) |  | LCC | Progressing. The accelerated delivery bid from Homes England, "forces" to deliver by March 2021 | query sent to agent for recent PCO app. LCC delays reason LCCs s106 not signed. Site has been marketed for some months with no apparent interest. Stated delivery to start from 21/22 building up to 50dpa | comments from LCC regarding holding off land sale due to CV19 (potential unrealistic expectations of land value/LCC return worries, failure to agree s106 for OUT since Aug 19. MMDR issues and potential delays. seeking HE extension, revising enabling works package. No developer interest in site which has been extensively marketed for a number of months and now withdrawn from marketing completely. Need to sell and REM and additional DIS etc. prior to SOS. potential competition other NSN sites may delay SOS given comments re return on investment. 40dpa as per statement accepted as reasonable completion rate | 4-5 years |  | 290 | 0 | 0 | 0 | 290 | [8 empty] | 10 | 30 | 50 | 50 | 50 | 50 | 50 | [7 empty] | 290 | 0
LP Allocation | Field OS 3968, Melton Spinney Road | Melton Mowbray | 200 | NSN (part) | 19/00208/REM (200) |  | Chave Planning (Caroline Chave) | The reserved matters application was submitted in February 2019 and is due for determination by 24th May 2019. Archaeological investigations have been undertaken and an application to discharge conditions is also pending. Subject to timely approval of the reserved matters application Taylor Wimpey would look to commence with enabling works in September 2019 and ground works in February 2020 A temporary sales outlet will be opened at the same time, with the anticipated completion for the show home in October 2020 and first completion in January 2021. | on site, construction started on show home | on site, construction started on show home, as recommended | U/C |  | 200 | 199 | 1 | 0 | 200 | REM passed, DIS submitted, SOS, advertised on website but as TBC |  | Taylor Wimpy (Kevin Bendall) | kevin.bendall@taylorwimpey.com | 20 | 47 | 47 | 46 | 40 | [13 empty] | 200 | 0
LP Allocation (w/o PP) | William Davis | Melton Mowbray | 175 | NSN (part) |  |  | William Davis Homes | They are keen to progress on an application ASAP for 200 dwellings (east of Scalford Road). Expected to start on site on February 2020. Masterplanning matters add uncertainty in this regard. | comments in line with those from other parties to master planning process. Aware MP is moving forwards within assumed timeframes. | assumed timeframe appears reasonable, however potential issues due to MMDR and TA progress that is required to move to OUT stage. Time assumed between OUT and REM approval considered short; especially so given issues in sorting S106 for other parts of NSN; assumed as recommended by developer + 12 months; to review against progress made next year | 4-5 years |  | 175 | 0 | 0 | 0 | 175 | [8 empty] | 30 | 50 | 50 | 45 | [10 empty] | 175 | 0
LP Allocation | Field OS 2713 2100, Longcliff Hill | Old Dalby | 36 | OLD1 | 18/01111/FUL (36) |  | HSSP (Mark Geraghty) |  | 20/00593/VAC 0620 PCO - minor mods and clarity re conditions; BC notice for plots 1-8 - works started | site observed as UC at site visits, activity to meet conditions and confirmed through feedback with agent, delivery as recommended | U/C |  | 36 | 0 | 2 | 0 | 36 |  |  |  |  | 12 | 12 | 12 | [15 empty] | 36 | 0
LP Allocation (w/o PP) | Land South of Melton Road | Scalford | 23 | SCAL1 |  |  | Shouler And Son (Simon Shouler) | Still available but has not applied for consent | no evidence of any actions being undertaken or planned in relation to this site | no interest in developing site at present | beyond 5 years |  | 23 | 0 | 0 | 0 | 23 | [13 empty] | 12 | 11 | [7 empty] | 23 | 0
LP Allocation | Field OS 3300, Oakham Road | Somerby | 32 | SOM1 | 20/00452/REM (PCO 31) | -1 | Mark Curtis-Bennett | Having been granted outline planning permission in April 2018 they submitted a reserve matters application in July 2018 but are still awaiting. They are keen to get full permission asap and start on site asap. Housing delivery obviously depends on obtaining full planning permission. | 18/00838/REM withdrawn site now with Taggart Homes. NEW 20/00452/REM (PCO) -21.04.2020 (16/00100/OUT for 32 dwellings, new REM for 31) | target decision date end July; then DIS; assumes SOS earliest Mar 2021 and then 14 month build programme as per statement. No dwellings no reduced until PCO REM decided | 1-2 years |  | 32 | 0 | 0 | 0 | 32 | [5 empty] | 4 | 20 | 8 | [14 empty] | 32 | 0
LP Allocation (w/o PP) | Land off High Street | Somerby | 42 | SOM2 |  |  | Greaves Project Management (Guy Greaves) | Application expected in 6 months for 10-15 houses, architects on board. Issues identified are: neighbourhood plan, planning committes decision, archaeological survey should be manageable | NP is moving forwards and at advanced stage however referendum not likely to be before need of 20/21 due to Coronavirus Act restrictions. | delay due to delayed adoption of NP likely (delayed referendum) as Trust want to bring forward site after adoption, unlikely to see application until 21/22, SOS before 22/23, completions assumed at 20dpa from 23/24 | 2-3 years |  | 42 | 0 | 0 | 0 | 42 | [7 empty] | 20 | 20 | 2 | [12 empty] | 42 | 0
LP Allocation (w/o PP) | Greenlight | Melton Mowbray | 850 | SSN(part) |  |  | Greenlight | It depends on the HIF as it depends on access. Consultants working towards an OUT to be sent on Christmas. It is expected to start by 2024/25 with a building rate of 72 dwellings per annum until 2034/35 and 58 on the last year of the Local Plan - this trajectory doesn't factor a successful HIF bid which will mean more delivery sooner on the site. The capacity of the site is not taken into account until further evidence is provided. | expect REM approval circa June 23 up to 72dpa trough till 2037/38 | as stated by developer based on detailed evidence provided recently for master planning | beyond 5 years |  |  | 0 | 0 | 0 | 850 | [8 empty] | 9 | 45 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 4 | 850 | 76
LP Allocation | Field OS 0002, Leicester Road | Melton Mowbray | 266 | SSN(part) | 19/00377/REM (266) |  | Bellway | Progressing towards Rem and also have submitted 19/00376/FUL for 60 dwellings for part of the site, still PCO. REM for the spine road connecting north and south is submitted too. | DN 29.11.2019, DIS applications submitted. BC IN submitted - for drainage works underway. Stated at committee where decided that SOS before end 2020 | site works are underway to enable SOS within next 12 months; developer led figures provided appear reasonable and delivery at an advanced scheme; noted that building out at higher rate than anticipated, therefore across a shorter overall build period | less than 12 months |  | 266 | 0 | 0 | 0 | 266 | [5 empty] | 52 | 88 | 79 | 44 | 3 | [12 empty] | 266 | 0
LP Allocation | Field OS 0002, Leicester Road | Melton Mowbray | 249 | SSN(part) | 19/00245/REM (PCO) |  | Barrats Homes | Archaeological investigations have recently concluded on site. In addition some hedge clearance took place in February 2019. No issues raised to date. Await decision on Reserved Matters Submission. Potential for numbers to fall, following initial officer comments. Development divided in 3 phases. REM for the spine road connecting north and south is submitted too. | Still PCO - Scheme 1 (19/00245/REM) EOT 010720; Scheme 2 (19/01099/REM) EOT 010820; refused and then deferred at committee; modifications have been made. Reasonable to assume DN within the next couple of months | As recommended, assumed REM granted this year for SOS next year, with completions up to 65dpa, building up to this figure with 50% in yr. 1 and delivered across a 5 year period. Comments re market signals influencing build rates mean have reduced to 50dpa as competition from other SSN sites may impact confidence to build at full 65dpa capacity | 1-2 years |  | 249 | 0 | 0 | 0 | 249 | [5 empty] | 32 | 50 | 50 | 50 | 50 | 17 | [11 empty] | 249 | 0
LP Allocation (w/o PP) | Davidsons | Melton Mowbray |  | SSN(part) | 16/00515/OUT (PCO) |  | Davidsons | Waiting for the HIF outcome, re-activating part of the site through 15/00127/OUT for 175 dwellings. Davidsons will develop the site so finding a developer is not an issue. As the number dwellings exceeds the allocation capacity (taking into account both REMs above), the capacity for the site is not taken into account until further evidence is provided | issues with MMDR and LCC may cause delays to achieving REM permission. Significant rent work by SSN developer to help develop masterplan for LCC adds to robustness of figures and assumptions | Figures provided by developer, however moved delivery onwards by 12 months to reflect potential for issues to delay delivery relating to MMDR etc. and given no action as yet to bring forwards to date which suggests more likely to be beyond 5 years; delivery has been adjusted down for this site over a longer period than suggested by developer; this has been undertaken for 2 reasons, high levels of annual delivery stated in comparison to other sites of the same size and in SSN and taking into consideration overall SSN delivery, to adjust the delivery across the period and reflect likely maximum capacity for sales across the SSN across the period (note this may mean other sites rather than this will deliver later in the period; however for the purposes of trajectory planning this site was adjusted as least advanced in terms of clear information on delivery and high stated delivery levels compared to others) | beyond 5 years |  | 355 | 0 | 0 | 0 | 355 | [9 empty] | 30 | 50 | 75 | 75 | 75 | 50 | [7 empty] | 355 | 0
LP Allocation (w/o PP) | Land west of Main Street | Stathern | 65 | STAT1 | 19/01302/FUL (PCO 74) |  | Pegasus (Guy Longley)/Davidsons | Towards PA (EIA Screening). Davidsons Developments Limited are working on the submission of a full planning application for the development of the site, with submission expected in early June 2019. A public exhibition was held on the 9th April 2019 and a pre-application meeting was held with officers on the 4th April 2019. The work on masterplanning to date indicates a capacity onsite of some 90 dwellings. | FUL submitted 1119 PCO by Pegasus/Davidsons; still PCO, issues re s106 and revised plan consultation. | Still PCO, recently revised plans need consultation; S106 required then DIS etc. developer ready to deliver; level of completions for 21/22 considered optimistic and proportion moved forwards; numbers not revised upwards as still PCO | 1-2 years |  | 65 | 0 | 0 | 0 | 65 | [5 empty] | 10 | 30 | 25 | [14 empty] | 65 | 0
LP Allocation | Levesley House , 14 City Road | Stathern | 8 | STAT2 | 18/00980/FUL (8) |  | Chave Planning (Caroline Chave) | Following full planning permission being granted in November 2018 the site has been marketed by Redmile Developments for custom-build plots. An application is being prepared for non-material amendments to the scheme to suit some of the purchasers' requirements. It is anticipated that development will commence in 2019 and will be completed in 2020/21 . | All under construction, 2 with windows, doors and roof, others at various stages. | All U/C | U/C |  | 8 | 0 | 6 | 2 | 6 |  |  |  |  | 6 | [17 empty] | 6 | 0
LP Allocation (w/o PP) | Land to the South East of Thorpe Road (A607) | Thorpe Arnold | 13 | THOR1 |  |  | Godfrey-Payton (Andrew Rusell-Wilks) | Developed alongside THOR2. Trent & Peak Archaeology were commissioned in 2018 to agree with Leicestershire County Council Archaeological unit a written scheme of investigation (WSI) for THOR1 to settle the archaeological constraints on the site. We need to know whether our planning application will be for 13 units or a greater number before we can submit it to your council. Despite chasing the County (Richard Clark) we have still not had a response. Trent & Peak Archaeology are chasing again this week. Any assistance Melton BC can give to unblock this problem would be very good. This has caused us six months delay from the trajectory we previously sent the Council. Suggested trajectory starts in 2020/21 | Potentially not deliverable due to archaeology issues 'site may be of regional archaeological importance' so either not deliverable or delivered with reduced numbers see 20/00531/ENQMG | Planning pre app enquiry stating deliverability issues. Numbers no amended until new permission granted. No permission in place, issues with bringing forward site, may require LP review to resolve? Archaeology likely to delay site delivery | beyond 5 years |  | 13 | 0 | 0 | 0 | 13 | [9 empty] | 6 | 7 | [11 empty] | 13 | 0
LP Allocation (w/o PP) | Land to the west of Thorpe Road (A607) | Thorpe Arnold | 11 | THOR2 | 0 |  | Godfrey-Payton (Andrew Rusell-Wilks) | Developed alongside THOR1. Trent & Peak Archaeology were commissioned in 2018 to agree with Leicestershire County Council Archaeological unit a written scheme of investigation (WSI) for THOR1 to settle the archaeological constraints on the site. We need to know whether our planning application will be for 13 units or a greater number before we can submit it to your council. Despite chasing the County (Richard Clark) we have still not had a response. Trent & Peak Archaeology are chasing again this week. Any assistance Melton BC can give to unblock this problem would be very good. This has caused us six months delay from the trajectory we previously sent the Council. Suggested trajectory starts at 2020/21 | see 20/00531/ENQMG; part of site served CPO by LCC to provide road improvements linked to MMDR roundabout close to site. Pre app submitted - expand site to accommodate CPO and THOR1 reduced numbers within enlarged site area | Planning pre app enquiry. CPO for part of site for MMDR. No planning for site to date. Want to significantly change allocated site in LP; may need to be through LP review; review next yr. after outcome of ENQMG | beyond 5 years |  | 11 | 0 | 0 | 0 | 11 | [9 empty] | 5 | 6 | [11 empty] | 11 | 0
LP Allocation | Land Behind 38 - 48, High Street | Waltham | 26 | WAL1 | 14/00777/FUL (26) |  | BHB Architects (Matthew Moran) | This development is not likely to go ahead for the foreseeable future as there has been a dispute with the landowner which is going to be difficult to resolve. | site was listed as 28 but always only 26? New 19/00453/FUL; 19/00479/NONMAT; 20/00092/NONMAT; 20/00489/DIS (PCO). All different agents/applicants -hello@jg-a.co.uk - James Garner on pending DIS contacted BURMOR projects ltd developer. Now 24 units plus 2 on separate application - 19/00453/FUL to main st frontage | Assume SOS in July, however pre commencement still PCO and concerns re getting site started due to Covid19, without to complete 24 within 8 month timeframe considered tight, therefore moved 1/3 delivery into 2021/22 | less than 12 months |  | 26 | 26 | 0 | 0 | 26 |  |  |  |  | 17 | 9 | [16 empty] | 26 | 0
LP Allocation | Fair Farm, 33 Melton Road | Waltham | 60 | WAL2 (part) | 18/01011/REM (PCO) |  | Boyer Planning (Laure McCombe) | RM considered at Planning committee on 4 April 2019, deferred for further discussion on materials. The completion figures below are subject to RM permission being granted by the end of April 2019. | our Site visits suggest 14 completed ( practically) at end of Mar compared to 2 stated by developer), however we use different definitions | work underway, 2/3 already U/C, at advanced stage; as recommended | U/C |  | 60 | 24 | 22 | 14 | 46 |  |  |  |  | 46 | [17 empty] | 46 | 0
LP Allocation | Field 1357, Melton Road | Waltham | 45 | WAL2 (part) | 17/00391/REM (45) |  | MHB Planning (Martin Bagshaw) |  | site visit suggested 5 not UC, contrary to developer statement, however site hard to view as closed; altered to all UC; recorded 5 blast year therefore 22 B in 1920 | site under construction, most plots at advanced stage of development | U/C | 5 | 40 | 0 | 18 | 22 | 18 |  |  |  |  | 18 | [17 empty] | 18 | 0
LP Allocation | Field No 4862, Glebe Road | Wymondham | 12 | WYM1 | 19/00827/REM (12) |  | Colin Wilkinson | the landowner who is hoping to exchange contracts in the next few weeks with Grace Homes. All being well, that will result in a Reserve Matters application soon afterwards. Grace Homes are keen to make a start as soon as possible and I would expect that to take place in 2019/20. Completion would be in 2020/21. Although the application details refer to ‘up to 15dw’ there is a condition limiting the site to 12dw. The landowner seems reasonably confident that things will progress in this way, but he has been here before with a different builder. | 19/00827/REM DN 17.12.2019. with 19/01309/DIS (PCO), new developer; Grace Homes | on site and ground works commenced | less than 12 months |  | 12 | 12 | 0 | 0 | 12 | [5 empty] | 12 | [16 empty] | 12 | 0
LP Allocation (w/o PP) | Remainder of Land off Butt Lane - NP development site 2 - station yard | Wymondham | 12 | WYM2 (part) | Remainder |  | Andrew Granger (Adam Murray) | No progress - phase 2 |  | not ready to submit any planning; least developed proposal for Wym | Beyond 5 years |  | 12 | 12 | 0 | 0 | 12 | [12 empty] | 6 | 6 | [8 empty] | 12 | 0
LP Allocation | Land Off Butt Lane - NP development site 1 | Wymondham | 9 | WYM2 (part) | 17/01575/FUL (9) |  | HSSP (Nick Cooper) | Progressing with initial four dwellings to building regulations | work started on site but low activity | construction underway on plots 1-4; delivery as recommended however adjustment as site visits confirmed that 2 dwl were practically complete at year end | U/C |  | 9 | 5 | 2 | 2 | 7 | [5 empty] | 7 | [16 empty] | 7 | 0
LP Allocation (w/o PP) | Land known as Brickyard Lane | Wymondham | 22 | WYM3 |  |  | Andrew Granger (Adam Murray) | An OUT is being prepared, which should be ready in June/July 2019. It needs to be sold to prospective developer |  | states looking to submit outline within next 12 months; not advanced enough to place in 5 year delivery | Beyond 5 years |  | 22 | 22 | 0 | 0 | 22 | [9 empty] | 11 | 11 | [11 empty] | 22 | 0
Large Site with PP | Land Opposite 1 And 10 Station Lane | Old Dalby | 72 |  | 17/00397/OUT |  | Colin Wilkinson | This permission (14/00954/OUT)) has effectively been replaced by 17/00397/OUT- Residential development of up to 72 dwellings. The site is brownfield and subject to contamination. Uncertainty over remediation is affecting developer interest, exacerbated by general market conditions, and therefore the landowner is undertaking further investigation works | 19/01319/DIS (PCO) | only has outline. Owner not progressing with pre construction investigations. No developer on board to proceed with site. REM expected by 3 years. Predict completions just beyond 5yhls, inputted completions at 20dpa as per developer provided information | beyond 5 years |  | 72 | 72 | 0 | 0 | 72 | [9 empty] | 20 | 20 | 20 | 12 | [9 empty] | 72 | 0
Large Site with PP | Field OS 3500, Hecadeck Lane | Nether Broughton | 25 |  | 15/01019/OUT (25) |  | Andrew Granger (Stephen Mair) | Currently in the process of selling the site - after that the REM | new applications 19/01379/VAC & 19/01380/VAC submitted 1219 & withdrawn 0420; Contact change as site sold to Grace Homes | sold to developer; Subject to new permission being granted | 1-2 years |  | 25 | 25 | 0 | 0 | 25 | [5 empty] | 4 | 16 | 5 | [14 empty] | 25 | 0
Large Site with PP | Land Adjacent The Woodlands, Station Road | Old Dalby | 25 |  | 16/00157/OUT (25) |  | Hofton and Son (Mark Shouler) | Progressing the site to reserved matters. There are certain conditions of the out line permission which need to be resolved/addressed. These are close now and we hope to be submitting for reserved matters this summer. Subject to the approval of the reserved matters we propose to start the site later part of next year. However this is all subject to planning Build rate difficult to answer, hoping to have funds to build approximately half the site assuming the site we are about to start sells well. if phase 1 at Old Dalby sells well, we will commence with phase 2 ASAP, all in all I would hope the site will be built in 2 years, however this may be optimistic. At this stage there are so many variables it is so difficult to predict including the impact of Brexit, we are currently concentrating on delivering a buildable planning consent; hoping to have clearer picture once obtained building consent. | 19/00735/ENQG pre app for REM, 0320. new contact mike asked - mike.askey@arcontext.com | REM yet to be submitted, pre app for REM undertaken and revised drawing for comments submitted and responded to 0320. SOS 21/22 possible but may be 22/23; developer is on board and leading REM. Potential for unknown/contamination etc. as former MOD land. Expect delivery from 22/23 not 21/22 given REM not yet submitted. | 1-2 years |  | 25 | 25 | 0 | 0 | 25 | [6 empty] | 20 | 5 | [14 empty] | 25 | 0
Large Site with PP | Land off Melton Road/Crompton Road | Asfordby Hill | 14 |  | 16/00907/OUT |  |  |  | 29.07.19 DN issued; Leicester Diocesan | only OUT; sale agreed but not gone through; REM needs to be worked up by new owner and permitted. Assume that this may mean the delivery more likely from 22/23 rather than in 21/22; more forwards assumptions provided by 12 months | 2-3 years |  | 14 | 14 | 0 | 0 | 14 | [6 empty] | 7 | 7 | [14 empty] | 14 | 0
Large Site with PP | War Memorial Hospital, Ankle Hill | Melton Mowbray | 98 |  | 19/01360/FUL (PCO +13) | 13 | David Wilson Homes |  | Sowden Homes developers, HSSP agent for PCO application, replace approved 18 with 31; +13 dwellings on the site | no change in dwelling numbers as +13 still PCO. Expect additional dwellings to be built quickly as already on site should PP be granted | U/C | 12 | 66 | 51 | 15 | 20 | 32 |  |  |  |  | 15 | 10 | 7 | [15 empty] | 32 | 0
Large Site with PP | Land West Of Bowling Green, Leicester Road | Melton Mowbray | 97 |  | 16/00290/FUL |  | Marrons (Graham Price) |  | no site visit information, based on info provided by agent. | Built | Built | 35 | 39 | 0 | 0 | 39 | 0 | [22 empty] | 0 | 0
Large Site with PP | Field 4100, Lake Terrace | Melton Mowbray | 90 |  | 20/00317/REM (PCO) (90) |  |  |  | Formerly 17/01500/OUT REM submitted 0320 - 20/00317/REM PCO alongside 20/00318/VAC & 20/00332/FUL both PCO; EQMG to increase dwellings, but not part of current REM, future revisions - site may offer phase 2 additional capacity from 2023/24 at stated 40dpa capacity | dependent on REM PCO, max build rate of 40dpa stated. | less than 12 months |  | 90 | 90 | 0 | 0 | 90 | [5 empty] | 40 | 40 | 10 | [14 empty] | 90 | 0
Large Site with PP | Spinney Campus - Brooksby Melton College, Melton Road | Brooksby | 70 |  | 19/01371/VAC |  |  |  | s73 VAR permitted 19/01371/VAC 260520. | Developer involved, but not tied to site, no date for sale etc. new owner may wish to reassess application post sale; brownfield site, potential additional clearance required before SOS. permission only just granted; No DIS etc. adjusted developer figures for first delivery in 22/23 rather than 21/22 as expect no SOS for at least 1 year given the above, built rate at 30dpa reasonable | 1-2 years |  | 70 | 70 | 0 | 0 | 70 | [6 empty] | 30 | 30 | 10 | [13 empty] | 70 | 0
Large Site with PP | Land West Of Marquis Road And North Of Station Road | Queensway | 39 |  | 18/01436/REM (39) |  | Rippon Homes Ltd | Currently awaiting times, dates and committee submission dates, even an indication of support from Joe Mitson and Jim Worley, deadline of tomorrow lunch. build rate as follows – 4 per month as to when we are expecting to start it will be approximately 12 weeks following the receipt of approval.time(18/4/19) set to hopefully get some sort of indication. However has been instructed to pursue an appeal route should this not be forth coming. - Update - Working towards the REM, which seems to be acceptable at this stage, subject to LLFA, AH and Highways comments | REM DN 300719 | REM granted; as recommended | 1-2 years |  | 39 | 39 | 0 | 0 | 39 | [6 empty] | 27 | 12 | [14 empty] | 39 | 0
Large Site with PP | Sandy Lane Poultry Farm | Melton Mowbray | 30 |  | 20/00438/REM (PCO 30) | 0 | Savills (UK) Limited (Maria Boyce) | Off on maternity leave, spoke with several people from Savills who were not able to give definitive answers as not aware of details. Also tried to contact Mr Adrian Office at Springbourne Homes but to no avail. | NEW 20/00438/REM (PCO). Now Springborne homes ltd & Hayward Architects still 30; 15/00537/OUT expired | taken 20 months as program as per developer, they are hopeful of autumn 20 start; assume completions from autumn 21 till summer 22 but adjusted for potential delay and caution as REM and DIS not in place as yet. 1/3 complete in 20/21 and remainder in 2021/22 | less than 12 months |  | 30 | 30 | 0 | 0 | 30 |  |  |  |  | 10 | 20 | [16 empty] | 30 | 0
Large Site with PP | Brooksby Melton College, King Street | Melton Mowbray | 21 |  | 16/00919/FUL (21) |  | WYG (Simon Chadwick) | Unable to contact. Site expiring in Jan/2021 - FUL application | Email sent to BMC to ask for update - no response. 19/01371/VAC for spinney campus, severed link between applications. Minutes from committee report - CEO of college state 'three organisations having approached the college with development proposals although due to the Covid 19 pandemic the position could not be confirmed'. She advised that one of the college’s requirements for any development was to retain the archaeological merits including the frontage.' Celia not aware of any ongoing interest from RPs. Info received via third party - agent for spinney road application | DN0118, will expire over course of this year. No developer on board, BMC reviewing options for the site. This has been situation for a number of years. Location, type of development, retention of historic frontage and lack of interest from developers for long period of time. considered likely to require further permission to exend or modify application now no longer an AH scheme | beyond 5 years |  | 21 | 21 | 0 | 0 | 21 | [9 empty] | 10 | 11 | [11 empty] | 21 | 0
Large Site with PP | Land West Of Bowling Green, Leicester Road | Melton Mowbray | 14 |  | 19/00217/FUL |  |  |  | BC initial 0419. Affordable housing EMH Homes. no site visit information, based on info provided by agent. | Under Construction | U/C |  | 14 | 0 | 14 | 0 | 14 |  |  |  |  | 14 | [17 empty] | 14 | 0
Large Site with PP | Southfields 10 Church Lane | Somerby | 12 |  | 20/00102/FUL (PCO 10) | -2 | Maurice Fairhurst | The site is advertised for sale (since Feb 17) but they are struggling to sell it. New application for less units (10) could include bungalows, written to architect. Issues related to the affordable housing requirement as it is putting builders off from purchasing the land, therefore they need to put forward a new application | previously 16/00146/OUT; PCO to go to com in July with recommendation to PER; Number of conditions inc arch to go through before can start to develop site if REM permitted; www.wynbrook.co.uk - developers have number of other projects underway with no publicity for this scheme on their website; if PCO REM PER contact developers directly next year; app description appears to assume enhanced building regulations - SOS post 2021 therefore assumed | REM not decided; likely number of conditions to fulfil before works can commence; no. units not reduced until REM permitted, remains 12; therefore moved delivery forwards slightly from 21/22 to 22/23; | 2-3 years |  | 12 | 11 | 0 | 0 | 12 | [6 empty] | 5 | 7 | [14 empty] | 12 | 0
Large Site with PP | The Old Vicarage, Leicester Road | Melton Mowbray | 10 |  | 19/00547/FUL |  |  |  | conditions discharge PCO 20/00354/DIS, construction started after end of financial yr. end for AM, so not UC in AM site visits. | under construction, conversion not new build, developers stated completion within 2020/21 reasonable | U/C |  | 10 | 10 | 0 | 0 | 10 |  |  |  |  | 10 | [17 empty] | 10 | 0
Large Site with PP | 3 Welby Lane | Melton Mowbray | 10 |  | 17/01391/FUL |  |  |  | BC - demolition and initial notice; DC - 19/00417/DIS decided 0619; Mr Dilip Parmar - ASKKD Ltd; dkparmar@hotmail.co.uk. Agent: Mr John Hackman -info@tdrarchitects.co.uk. Noise complaint about construction noise from Jan 2020 - suggests that site is under construction. site visit officer stated not under construction; suggest at site works stage of development, pre commencement works. CH charge of mortgage against company, more likely that development to come forwards to meet mortgage terms and conditions of loan to buy and develop the site. | Some works appear to have started on site (noise complaint Mar 20 within DIS files and BC initial notices from mid 2019). Developer failed to respond so assumptions have been made based on site visit info and BC notices, inferred that site is close to starting to construction and that development will start in 2020, assuming all 10 completions in 21/22 given lack of certainty about how advanced the site is at this time | less than 12 months |  | 10 | 10 | 0 | 0 | 10 | [5 empty] | 10 | [16 empty] | 10 | 0
Large Site with PP | 42 Main Road | Nether Broughton | 10 |  | 16/00577/FUL |  | Trevor Muir Ltd | the building work for this site is due to start in afew months with completion expected early / mid 2020 (January 2018) (Still N/S by April 2018) | demolishment started - BC - 20/00052/DEM; Cairn Heritage Homes website states homes coming soon | Ground works commenced, homes advertised; could change, depending on economy/demand, impact so far not clear | less than 12 months |  | 10 | 10 | 0 | 0 | 10 |  |  |  |  | 5 | 5 | [16 empty] | 10 | 0
Small site with PP | Rydal Manor, Kirby Lane | Eye Kettleby | 9 |  | 17/00962/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 6 | 3 | 0 | 0 | 3 | 0 | [22 empty] | 0 | 0
Large Site with PP | 75 Welby Lane | Melton Mowbray | 9 |  | 16/00708/FUL |  | Angela Rennie (HSSP) | DIS submitted, building regulations for first 4 instructed and others will depend on funding | BC notices for refurb and extension of no. 75 not replacement. 20/00223/DIS PCO for drainage and landscaping etc. as 75 retained site now only for 9 dwellings; remove from large sites | Majority of site needs to be sold to developer | less than 12 months (part) |  | 10 | 9 | 0 | 0 | 9 |  |  |  |  | 2 |  | 7 | [15 empty] | 9 | 0
Small site with PP | 3 Welby Lane | Melton Mowbray | 9 |  | 17/01391/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 10 | 4 | 6 | 0 | 10 |  |  |  |  | 6 | 4 | [16 empty] | 10 | 0
Small site with PP | The Paddock, Dalby Road | Nether Broughton | 9 |  | 17/00636/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 9 | 9 | 0 | 0 | 9 | [6 empty] | 3 | 3 | 3 | [13 empty] | 9 | 0
Small site with PP | Field OS 6604, Nottingham Road | Ab Kettleby | 8 |  | 18/01419/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 8 | 8 | 0 | 0 | 8 | [6 empty] | 3 | 3 | 2 | [13 empty] | 8 | 0
Small site with PP | Land Adjacent Rydal Manor, Kirby Lane | Eye Kettleby | 8 |  | 19/00858/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 8 | 8 | 0 | 0 | 8 | [6 empty] | 3 | 3 | 2 | [13 empty] | 8 | 0
Small site with PP | Land Adjacent 7, Ashby Road | Gaddesby | 8 |  | 19/01073/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 8 | 8 | 0 | 0 | 8 | [6 empty] | 3 | 3 | 2 | [13 empty] | 8 | 0
Small site with PP | North Lodge Farm, Longcliff Hill | Old Dalby | 8 |  | 16/00911/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 8 | 8 | 0 | 0 | 8 | [6 empty] | 3 | 3 | 2 | [13 empty] | 8 | 0
Small site with PP | Longcliffe Hill House, Longcliff Hill | Old Dalby | 8 |  | 17/00315/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 8 | 8 | 0 | 0 | 8 | [6 empty] | 3 | 3 | 2 | [13 empty] | 8 | 0
Small site with PP | Land To South Of 1 Tilton Road, Tilton Road | Twyford | 8 |  | 15/00935/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 6 | 2 | 0 | 0 | 2 | 0 | [22 empty] | 0 | 0
Small site with PP | 88 Dalby Road | Melton Mowbray | 7 |  | 16/00898/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 7 | 7 | 0 | 0 | 7 | [6 empty] | 3 | 3 | 1 | [13 empty] | 7 | 0
Small site with PP | Beebys Yard, Burton Street | Melton Mowbray | 7 |  | 08/00326/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 7 | 3 | 4 | 0 | 7 |  |  |  |  | 4 | 3 | [16 empty] | 7 | 0
Small site with PP | Land At East Lodge Longcliff Hill | Old Dalby | 7 |  | 17/00743/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 7 | 4 | 0 | 3 | 4 | [5 empty] | 4 | [16 empty] | 4 | 0
Small site with PP | Grantham Road | Bottesford | 6 |  | 15/00854/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 6 | 6 | 0 | 0 | 6 | [6 empty] | 3 | 3 | [14 empty] | 6 | 0
Small site with PP | Field 3957, Manor Road | Easthorpe | 6 |  | 16/00352/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 6 | 6 | 0 | 0 | 6 | [6 empty] | 3 | 3 | [14 empty] | 6 | 0
Small site with PP | Equity House, 47 Burton Street | Melton Mowbray | 6 |  | 16/00116/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 6 | 0 | 0 | 6 | 0 | [22 empty] | 0 | 0
Small site with PP | Land Adjacent 7, Ashby Road | Gaddesby | 5 |  | 12/00530/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 5 | 5 | 0 | 0 | 5 | [6 empty] | 3 | 2 | [14 empty] | 5 | 0
Small site with PP | North Lodge Farm Longcliff Hill | Old Dalby | 5 |  | 18/00568/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 5 | 5 | 0 | 0 | 5 | [6 empty] | 3 | 2 | [14 empty] | 5 | 0
Small site with PP | Merrivale Farm, 18 Frog Lane | Plungar | 5 |  | 13/00683/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 5 | 5 | 0 | 0 | 5 | [6 empty] | 3 | 2 | [14 empty] | 5 | 0
Small site with PP | 36 Wartnaby Road | Ab Kettleby | 4 |  | 17/01597/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | The Old Hall 146 Main Street | Asfordby | 4 |  | 18/00666/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | Headland House Farm, Great Dalby Road | Ashby Folville | 4 |  | 18/00998/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 0 | 0 | 4 | 0 | [22 empty] | 0 | 0
Small site with PP | Land Adjacent Deven Farm | Bottesford | 4 |  | 16/00121/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 2 | 2 | 0 | 0 | 2 | 0 | [22 empty] | 0 | 0
Small site with PP | Land off, Station Road | Bottesford | 4 |  | 17/01549/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | Vale End House, Green Lane | Easthorpe | 4 |  | 18/01240/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 3 | 0 | 1 | 3 | [5 empty] | 3 | [16 empty] | 3 | 0
Small site with PP | Land Off Main Street | Eaton | 4 |  | 17/00837/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 0 | 1 | 3 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Land Adjacent 54 Barkers Farm, Church Lane | Long Clawson | 4 |  | 19/00700/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | Field OS 5855 And 6071, Nottingham Road | Melton Mowbray | 4 |  | 19/00266/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | King Edward Vii Upper School, Burton Road | Melton Mowbray | 4 |  | 18/00202/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | Beebys Yard, Burton Street | Melton Mowbray | 4 |  | 19/01175/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 0 | 4 | 0 | 4 |  |  |  |  | 4 | [17 empty] | 4 | 0
Small site with PP | Manor Farm, 32 Main Street | Muston | 4 |  | 16/00692/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 2 | 2 | 0 | 2 | 0 | 2 |  |  |  |  | 2 | [17 empty] | 2 | 0
Small site with PP | The Limes Farm, 37 Middle Lane | Nether Broughton | 4 |  | 15/00220/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | 1 Station Lane | Old Dalby | 4 |  | 15/00881/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | Butlers Cottage, 11 Somerby Road | Pickwell | 4 |  | 17/01389/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 5 | 5 | 0 | 0 | 5 | [6 empty] | 3 | 2 | [14 empty] | 5 | 0
Small site with PP | Westfield 24 The Field | Somerby | 4 |  | 15/00149/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | The Granary, Branston Road | Eaton | 3 |  | 18/00858/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Sunningdale 25 Top End | Great Dalby | 3 |  | 18/00381/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Land Adjacent 51 Stathern Lane | Harby | 3 |  | 18/00044/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 1 | 2 | 2 | 0 | 0 | 2 | [5 empty] | 2 | [16 empty] | 2 | 0
Small site with PP | Land At Cottage Farm, 36 Main Road | Kirby Bellars | 3 |  | 17/01312/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | The Shires, 26 Church Lane | Long Clawson | 3 |  | 08/00703/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | Hose Lodge, Canal Lane | Long Clawson | 3 |  | 17/01547/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 4 | 4 | 0 | 0 | 4 | [6 empty] | 3 | 1 | [14 empty] | 4 | 0
Small site with PP | 35 Scalford Road | Melton Mowbray | 3 |  | 15/00630/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 0 | 0 | 3 | 0 | [22 empty] | 0 | 0
Small site with PP | Sandy Lane Farm Buildings, Sandy Lane | Melton Mowbray | 3 |  | 16/00232/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 2 | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Potterhill Farm, 12 Potter Hill Nottingham Road | Melton Mowbray | 3 |  | 17/00131/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Land Off Middle Lane | Nether Broughton | 3 |  | 17/00950/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Lodge Farm, Dalby Road | Nether Broughton | 3 |  | 18/01339/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Land Adjacent 2 Queensway | Queensway | 3 |  | 17/00478/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Overfields, 1 Belvoir Road | Redmile | 3 |  | 17/00030/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Land Parcel, School Lane | Sewstern | 3 |  | 16/00596/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 1 | 0 | 2 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Greengates Farm 23 Main Street | Sproxton | 3 |  | 16/00538/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Land Adj Woodbine Farm, Main Road | Wyfordby | 3 |  | 17/00044/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | 39 Edmondthorpe Road | Wymondham | 3 |  | 17/00446/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Old School House, 2A Church Lane | Wymondham | 3 |  | 19/00685/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Field 7318 Melton Road | Ab Kettleby | 2 |  | 18/00790/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Ashby Pastures | Ashby Folville | 2 |  | 17/00437/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 1 | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Field OS 8900 Folville Street | Ashby Folville | 2 |  | 18/01435/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Little Jacks Farm and Garden Centre, Orston Lane | Bottesford | 2 |  | 18/00836/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Buildings At The Rear Of 11, Main Street | Branston | 2 |  | 16/00765/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Lings Farm, Lings Hill | Croxton Kerrial | 2 |  | 19/00383/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Easthorpe Lodge, Manor Road | Easthorpe | 2 |  | 19/01340/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Eastwell Hall, 3 Hall Lane | Eastwell | 2 |  | 17/00001/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 3 | 3 | 0 | 0 | 3 | [6 empty] | 3 | [15 empty] | 3 | 0
Small site with PP | Glebe Farm, Waltham Lane | Eaton | 2 |  | 18/01462/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | The White Lodge, Green Lane | Goadby Marwood | 2 |  | 17/00013/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Land South Of Stathern Lane | Harby | 2 |  | 18/00775/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 1 | 1 | 0 | 2 |  |  |  |  | 1 | 1 | [16 empty] | 2 | 0
Small site with PP | Culfers Hey, 2 Melton Road | Long Clawson | 2 |  | 11/00632/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 1 | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Land off 9 Melton Road | Long Clawson | 2 |  | 18/00984/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | 11 East End | Long Clawson | 2 |  | 19/00861/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Park Lane Public Conveniences | Melton Mowbray | 2 |  | 17/00571/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | 1 Charnwood Drive | Melton Mowbray | 2 |  | 17/01512/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Land To North Of Beckmill Court | Melton Mowbray | 2 |  | 18/00299/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Young Swistak Solicitors, 56 Nottingham Street | Melton Mowbray | 2 |  | 19/00740/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Plot Of Land At Nottingham | Old Dalby | 2 |  | 18/01133/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Brick Barns Adj To Old Hall Farm, Six Hills Road | Ragdale | 2 |  | 19/00373/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 0 | 2 | 0 | -2 | 2 | [5 empty] | 2 | [16 empty] | 2 | 0
Small site with PP | Brick Barns Adj To Old Hall Farm, Six Hills Road | Ragdale | 2 |  | 19/01034/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Brook Farm, 1 Church Lane | Saxelby | 2 |  | 15/00311/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Cranyke Farm Eastwell Road | Scalford | 2 |  | 18/00785/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 0 | 2 | 0 | 2 |  |  |  |  | 2 | [17 empty] | 2 | 0
Small site with PP | Cranyke Farm, Eastwell Road | Scalford | 2 |  | 19/01283/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 0 | 2 | 0 | 2 |  |  |  |  | 2 | [17 empty] | 2 | 0
Small site with PP | Somerby House Cottage, 3 High Street | Somerby | 2 |  | 17/00763/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Greengates Farm 23 Main Street | Sproxton | 2 |  | 16/00536/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Farm Buildings Adjacent Stapleford Cross, Glebe Road | Stapleford | 2 |  | 18/01162/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Levesley House 14 City Road | Stathern | 2 |  | 17/00587/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 0 | 0 | 2 | 0 | [22 empty] | 0 | 0
Small site with PP | Land Rear Of Folville House, Main Street | Stathern | 2 |  | 18/01443/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 1 | 1 | 0 | 2 |  |  |  |  | 1 | 1 | [16 empty] | 2 | 0
Small site with PP | Land Adjacent 48 High Street | Waltham | 2 |  | 13/00290/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Land Between 42 And 48 High Street | Waltham on the Wolds | 2 |  | 19/00453/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Manns Farm, 66 Main Street | Wymondham | 2 |  | 19/01029/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Former Agricultural Building Off Welby Lane Ab Kettleby | Ab Kettleby | 1 |  | 18/00203/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | The Old Hall 146 Main Street | Asfordby | 1 |  | 18/00669/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land To North Of Bypass Road | Asfordby | 1 |  | 18/01316/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | The Grange Garden Centre | Asfordby Hill | 1 |  | 06/00302/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | The Lodge, Gaddesby Lane | Ashby Folville | 1 |  | 16/00202/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | Headland House Farm, Great Dalby Road | Ashby Folville | 1 |  | 18/00477/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Agricultural Barn, Stable Cottage, Pasture Lane | Ashby Folville | 1 |  | 18/00957/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 7 Highfield End | Ashby Folville | 1 |  | 18/00575/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 17 Main Street | Barsby | 1 |  | 15/00470/FULHH |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Barsby Farm 11 Main Street | Barsby | 1 |  | 16/00142/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Barsby Farm 11 Main Street | Barsby | 1 |  | 16/00143/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Land To The South Of The Lane | Barsby | 1 |  | 19/00396/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Barn At Barsby Lodge Farm | Barsby | 1 |  | 17/01492/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land To The South Of The Lane | Barsby | 1 |  | 18/00813/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land To The South Of The Lane | Barsby | 1 |  | 18/01153/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Walnut Tree Farm, 17 Main Street | Barsby | 1 |  | 19/00062/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 2 Vaughan Avenue | Bottesford | 1 |  | 18/01088/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | 25 Nottingham Road | Bottesford | 1 |  | 18/01012/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 20 Main Street | Branston | 1 |  | 16/00360/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Brooksby Grange, Melton Road | Brooksby | 1 |  | 17/00864/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Pasture Farm House 5 Kings Lane | Burrough on the Hill | 1 |  | 18/00753/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Storehouse Farm, 50 Main Street | Cold Overton | 1 |  | 17/00252/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Gates Nurseries, Somerby Road | Cold Overton | 1 |  | 16/00345/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land Between 18 And 20, Main Street | Cold Overton | 1 |  | 15/00445/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Field Nos 9878 And 0868, Main Street | Cold Overton | 1 |  | 17/01104/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Land Between 14 And 20 Church Lane | Croxton Kerrial | 1 |  | 05/00767/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Church End , 29 Middle Street | Croxton Kerrial | 1 |  | 17/01253/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | The Bungalow, 2 Chapel Lane | Croxton Kerrial | 1 |  | 19/00986/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | 8 Manor Road | Easthorpe | 1 |  | 17/00208/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land To The North Of 8 Manor Road | Easthorpe | 1 |  | 18/00103/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Longridge, Castle View Road | Easthorpe | 1 |  | 18/00812/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | 12 Castle View Road | Easthorpe | 1 |  | 19/00925/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Ivy House Farm, 3 Elm Lane | Eaton | 1 |  | 15/00191/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Hall Farm House, The Driveway | Eye Kettleby | 1 |  | 17/00608/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Parwood House, 22 Main Street | Frisby On The Wreake | 1 |  | 15/00824/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 24 Mill Lane | Frisby On The Wreake | 1 |  | 17/01182/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | South of 25 Mill Lane | Frisby On The Wreake | 1 |  | 17/00441/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Old Mill, 25 Mill Lane | Frisby On The Wreake | 1 |  | 16/00639/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Land Adj The Hall, Main Street | Gaddesby | 1 |  | 17/01139/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Hall, 2 Main Street | Gaddesby | 1 |  | 15/00826/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Hall, 2 Main Street | Gaddesby | 1 |  | 19/00525/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Park House Cottage, 12 Ashby Road | Gaddesby | 1 |  | 19/01250/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Methodist Church, 6 Towns Lane | Goadby Marwood | 1 |  | 17/00932/COU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Field OS 6532, Main Street | Goadby Marwood | 1 |  | 19/00989/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Brook Farm, 8 Nether End | Great Dalby | 1 |  | 17/01297/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land at 12A, Nether End | Great Dalby | 1 |  | 17/00856/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Land Adjacent To 7 Main Street | Great Dalby | 1 |  | 18/01345/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Stable Conversion, Main Street | Grimston | 1 |  | 17/00039/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Oakley Cottages, 20 Main Street | Grimston | 1 |  | 19/00952/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land Adjacent 29 Watsons Lane | Harby | 1 |  | 17/00037/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Hill Farm, Waltham Lane | Harby | 1 |  | 18/01073/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land To The Rear Of No 3 Nether Street | Harby | 1 |  | 18/00909/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Homelands, 4 Dickmans Lane | Harby | 1 |  | 19/00878/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Granary, Thrussington Road | Hoby | 1 |  | 17/00480/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | The Old Rutland 6 Regent Road | Hoby | 1 |  | 18/00494/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Barn At Field OS 2245, Main Street | Holwell | 1 |  | 17/01490/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Holwell Lodge, Clawson Road | Holwell | 1 |  | 18/00594/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 2A Main Street | Holwell | 1 |  | 19/00661/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Rutland House, 4 Dairy Lane | Hose | 1 |  | 17/00185/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Plot 5, Canal Lane | Hose | 1 |  | 17/00581/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Station House, Station Road | John O Gaunt | 1 |  | 15/00710/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Jubilee House, Station Road | John O Gaunt | 1 |  | 17/01508/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Field OS 0850, Gaddesby Lane | Kirby Bellars | 1 |  | 17/00140/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | OS Field 5854, Cold Overton Road | Knossington | 1 |  | 18/01140/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Pheasant Cottage, 55 Church Lane | Long Clawson | 1 |  | 14/00897/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Chestnut Cottage, 17 West End | Long Clawson | 1 |  | 19/00104/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Barn at Highfield Farm, Hose Lane | Long Clawson | 1 |  | 19/00851/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land To North Of 175 Scalford Road | Melton Mowbray | 1 |  | 13/00646/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 137 Asfordby Road | Melton Mowbray | 1 |  | 14/00128/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 11 Nottingham Road | Melton Mowbray | 1 |  | 14/00760/FUL |  |  |  | n/a | Small site with PP | Within 5 years | 2 | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0 | 0
Small site with PP | 63 Ankle Hill | Melton Mowbray | 1 |  | 15/00286/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 75 Welby Lane | Melton Mowbray | 1 |  | 15/00885/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 2 | 0 | 0 | 2 | [6 empty] | 2 | [15 empty] | 2 | 0
Small site with PP | School Bungalow, Dalby Road | Melton Mowbray | 1 |  | 15/00941/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 91 Thorpe Road | Melton Mowbray | 1 |  | 17/01109/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 49 Valley Road | Melton Mowbray | 1 |  | 18/00207/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 57 Regent Street | Melton Mowbray | 1 |  | 18/01032/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 0 | 0 | 2 | 0 | [22 empty] | 0 | 0
Small site with PP | Land To Rear Of 43 Blyth Avenue | Melton Mowbray | 1 |  | 18/01433/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | 72 Princess Drive | Melton Mowbray | 1 |  | 19/00032/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Wyndham Lodge, Kennelmore Road | Melton Mowbray | 1 |  | 19/00020/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 4 | 0 | -3 | 4 | [5 empty] | 2 | 2 | [15 empty] | 4 | 0
Small site with PP | Forresters Hall, Rosebery Avenue | Melton Mowbray | 1 |  | 19/00696/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land Opposite Old Rectory, Church End | Nether Broughton | 1 |  | 16/00055/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Barn At Elm Farm, Main Street | Normanton | 1 |  | 17/01272/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Proposed Flexible Workspace Units, Station Road | Old Dalby | 1 |  | 14/00064/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Lodge Farm, Six Hills Lane | Old Dalby | 1 |  | 14/00422/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land Behind 11, Debdale Hill | Old Dalby | 1 |  | 16/00441/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 11 Paradise Lane | Old Dalby | 1 |  | 17/00274/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Reservoir At Six Hills Lane | Old Dalby | 1 |  | 18/00633/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Debdale Hill House, 8 Debdale Hill | Old Dalby | 1 |  | 18/00816/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | North Lodge Farm Longcliff Hill | Old Dalby | 1 |  | 18/00506/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land Adj To No 11 And 13 Paradise Lane | Old Dalby | 1 |  | 18/00919/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Field OS 1342, Church Lane | Old Dalby | 1 |  | 19/00679/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Stables At Vale View Farm, Nottingham Lane | Old Dalby | 1 |  | 19/01078/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Chestnuts, 12 Belvoir Road | Redmile | 1 |  | 12/00914/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Bishops Lodge, 6 Main Street | Saltby | 1 |  | 16/00698/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Croxton View, 35 Main Street | Saltby | 1 |  | 19/00056/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Brook Farm, 1 Church Lane | Saxelby | 1 |  | 17/00147/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Brook Farm, 1 Church Lane | Saxelby | 1 |  | 17/01566/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Rosary , 9 Main Street | Saxelby | 1 |  | 16/00737/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Brook Farm, 1 Church Lane | Saxelby | 1 |  | 18/00629/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Field OS 2900, Main Street | Saxelby | 1 |  | 19/00703/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | The Bungalow, 2 Sandy Lane | Scalford | 1 |  | 14/00327/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 2 | 0 | 2 | 0 | 2 |  |  |  |  | 2 | [17 empty] | 2 | 0
Small site with PP | Horsepool Cottage 7 New Street | Scalford | 1 |  | 18/00008/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Bellemere Farm, Eastwell Road | Scalford | 1 |  | 19/00554/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Linden Lodge, Holwell Lane | Scalford | 1 |  | 19/01002/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 54 Main Street | Sewstern | 1 |  | 07/00636/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Aylesford Farm, Main Street | Shoby | 1 |  | 19/00543/GDOCOU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Land Rear Of 2 Town End | Somerby | 1 |  | 16/00679/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | The Old Stables 22 High Stret | Somerby | 1 |  | 18/00402/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Field 3465 Coston Road | Sproxton | 1 |  | 14/00978/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Field Os 1721 Coston Road | Sproxton | 1 |  | 15/00873/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Land Adjacent The Barn, Stonesby Road | Sproxton | 1 |  | 16/00797/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 7 City Road | Stathern | 1 |  | 15/00569/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land Off Harby Road | Stathern | 1 |  | 16/00870/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land Adjacent To Hillcrest, Tofts Hill | Stathern | 1 |  | 16/00956/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 8A Penn Lane | Stathern | 1 |  | 17/01036/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | 27 Main Street | Stathern | 1 |  | 18/01303/COU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Caravan At Baileys Farm, Mill Hill | Stathern | 1 |  | 18/01119/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 6B Penn Lane | Stathern | 1 |  | 18/00488/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | The Old Rectory, 8 Water Lane | Stathern | 1 |  | 19/00321/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Hindle Top Farm, Melton Spinney Road | Thorpe Arnold | 1 |  | 18/00030/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | De Bosco House, Waltham Road | Thorpe Arnold | 1 |  | 19/00284/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 34 Main Street | Thorpe Satchville | 1 |  | 16/00120/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | 34 Main Street | Thorpe Satchville | 1 |  | 19/00811/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Brook House , 6 Main Road | Twyford | 1 |  | 17/00352/OUT |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Brook House, 6 Main Road | Twyford | 1 |  | 19/00241/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Harvest Home, 3 Melton Road | Waltham | 1 |  | 15/00347/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Land At 3 Melton Road | Waltham on the Wolds | 1 |  | 19/00074/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | High Burnham, 46 Melton Road | Waltham on the Wolds | 1 |  | 11/00775/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | 3 Spring Lane | Wartnaby | 1 |  | 16/00497/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Navvies Cottage Butt Lane | Wymondham | 1 |  | 17/00666/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Workshop, Edmondthorpe Road | Wymondham | 1 |  | 18/01280/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Cedar Lodge, 32 Great lane | Frisby On The Wreake | 0 |  | 18/01313/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Kirby Gate, 1 Main Road | Kirby Bellars | 0 |  | 16/00770/COU |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | 33 Dalby Road | Melton Mowbray | 0 |  | 19/00132/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Cedar Bungalow, 44 Main Road | Old Dalby | 0 |  | 16/00622/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 0
Small site with PP | Meadow View, Nottingham Lane | Old Dalby | 0 |  | 19/00808/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Corona Cottage, 11 Sandy Lane | Scalford | 0 |  | 14/00395/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Woodville 4 Dalliwell | Stathern | 0 |  | 16/00874/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 1 | 0 | 0 | 1 | [5 empty] | 1 | [16 empty] | 1 | 0
Small site with PP | Covert Farm Garthorpe lane | Waltham | 0 |  | 16/00502/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | 1 | 0 | 0 | 1 | 0 | [22 empty] | 0 | 0
Small site with PP | Engine Yard House, Woolsthorpe Road | Belvoir | -1 |  | 18/00723/FUL |  |  |  | n/a | Small site with PP | Within 5 years |  | -1 | 0 | 0 | -1 | 0 | [22 empty] | 0 | 0
Windfall allowance |  | n/a | [6 empty] | 29 dpa unless this is already met | Windfall allowance | [6 empty] | 334 |  |  |  |  | 0 | 0 | 0 | 0 | 15 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 |  |  | 334 | 0
TOTAL | [16 empty] | 7005 | 0 | 0 | 0 | 0 | 368 | 714 | 835 | 646 | 558 | 579 | 565 | 528 | 447 | 434 | 364 | 202 | 166 | 161 | 203 | 159 | 72 | 4 | 7005 | 76
[22 empty] | 177 | 274 | 424 | 356 | 314 | 407 | 459 | 452 | 405 | 405 | 323 | 162 | 137 | 122 | 144 | 100